## Overview
RedditSummit – 3-Sprint Plan
Team: Jalal, Khan, Wesley, Ayman ¦ Plan window: 9/22/2026 – 11/19/2026
Sprint | Start | End | Days | Goal | Check-in dates | Points | Est. Hrs
Sprint 1 | 2026-09-22 | 2026-10-11 | 20 | Foundation: accounts, login, create post, post feed | 9/28, 10/2, 10/6, 10/10 | 20 | 92
Sprint 2 | 2026-10-12 | 2026-10-31 | 20 | Discussion: replies, category filter, anonymous posting, my activity | 10/16, 10/20, 10/24, 10/29 | 26 | 86
Sprint 3 | 2026-11-01 | 2026-11-19 | 19 | AI summary twist, likes, testing, final demo | 11/5, 11/9, 11/13, 11/17 | 26 | 105
Total | [5 empty] | 72 | 283
Workload by member
Member | S1 Points | S2 Points | S3 Points | Total Points | S1 Hrs | S2 Hrs | S3 Hrs | Total Hrs
Jalal | 5 | 8 | 8 | 21 | 24 | 24 | 23 | 71
Khan | 5 | 8 | 5 | 18 | 23 | 24 | 20 | 67
Wesley | 5 | 5 | 5 | 15 | 22 | 20 | 20 | 62
Ayman | 5 | 5 | 5 | 15 | 23 | 18 | 16 | 57
All (team story) | 0 | 0 | 3 | 3 | 0 | 0 | 26 | 26
Total | 20 | 26 | 26 | 72 | 92 | 86 | 105 | 283
Assumptions & notes
• Sprint lengths: S1 20 days, S2 20 days, S3 19 days; each sprint ends with a review & retrospective (S3 ends with the final demo on 11/19).
• Points use a Fibonacci scale (3/5/8); hours are initial team estimates — adjust them in the sprint tabs during planning.
• AI summary reply threshold is assumed to be 5 replies (the backlog doesn't set a number) — confirm with the team.
• 'Like a post' and 'Like a comment' come from the workflow diagram but are not in the product backlog; they are planned last (Sprint 3) so they can be dropped if time runs short.
• Sprint order builds dependencies first: accounts → posts → replies/categories → anonymous posting → AI summary.
• How to use: fill Hrs Left on task rows in each Sprint tab at every check-in; story rows, totals, and this overview update automatically.

## Schedule
RedditSummit – Sprint Schedule (9/22/2026 – 11/19/2026)
Bars are colored by owner. Gray columns are weekends. ◆ = sprint review / milestone. Change Start/End dates and the bars move.
[6 empty] | September 2026 | [8 empty] | October 2026 | [30 empty] | November 2026
[6 empty] | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Sprint | Owner | Work item | Start | End | Days | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19
Sprint 1 |  | Foundation: accounts, login, create post, post feed | 2026-09-22 | 2026-10-11 | 20
S1 | Jalal | As a user, I can register for an account with a unique username and email. | 2026-09-22 | 2026-10-10 | 19
S1 | Jalal | Set up backend project, database, and users table | 2026-09-22 | 2026-09-26 | 5
S1 | Jalal | Build registration API with password hashing and duplicate checks | 2026-09-27 | 2026-10-01 | 5
S1 | Jalal | Create registration screen UI | 2026-10-02 | 2026-10-05 | 4
S1 | Jalal | Add input validation and error messages | 2026-10-06 | 2026-10-07 | 2
S1 | Jalal | Review & check-in | 2026-10-08 | 2026-10-10 | 3
S1 | Jalal | Document | 2026-10-06 | 2026-10-10 | 5
S1 | Wesley | As a user, I can log in and stay logged in while I use the app. | 2026-09-22 | 2026-10-10 | 19
S1 | Wesley | Build login API with token-based session | 2026-09-22 | 2026-09-26 | 5
S1 | Wesley | Create login screen UI | 2026-09-27 | 2026-09-30 | 4
S1 | Wesley | Persist session across app restarts and add logout | 2026-10-01 | 2026-10-03 | 3
S1 | Wesley | Require login before creating posts or replies | 2026-10-04 | 2026-10-07 | 4
S1 | Wesley | Review & check-in | 2026-10-08 | 2026-10-10 | 3
S1 | Wesley | Document | 2026-10-06 | 2026-10-10 | 5
S1 | Khan | As a user, I can create a post with a title, description, and category. | 2026-09-22 | 2026-10-10 | 19
S1 | Khan | Create posts and categories tables; seed predefined categories | 2026-09-22 | 2026-09-25 | 4
S1 | Khan | Build create-post API (logged-in users only) | 2026-09-26 | 2026-09-29 | 4
S1 | Khan | Create post composer screen with category picker | 2026-09-30 | 2026-10-04 | 5
S1 | Khan | Validate title, description, and required category | 2026-10-05 | 2026-10-07 | 3
S1 | Khan | Review & check-in | 2026-10-08 | 2026-10-10 | 3
S1 | Khan | Document | 2026-10-06 | 2026-10-10 | 5
S1 | Ayman | As a user, I can browse posts created by other users in a feed. | 2026-09-22 | 2026-10-10 | 19
S1 | Ayman | Set up mobile app skeleton and screen navigation | 2026-09-22 | 2026-09-25 | 4
S1 | Ayman | Build feed API (newest first, paginated) | 2026-09-26 | 2026-09-29 | 4
S1 | Ayman | Create feed screen with post cards (title, category, author, reply count) | 2026-09-30 | 2026-10-04 | 5
S1 | Ayman | Add pull-to-refresh plus loading and empty states | 2026-10-05 | 2026-10-07 | 3
S1 | Ayman | Review & check-in | 2026-10-08 | 2026-10-10 | 3
S1 | Ayman | Document | 2026-10-06 | 2026-10-10 | 5
S1 | All | ◆ Sprint 1 review & retrospective | 2026-10-11 | 2026-10-11 | 1
Sprint 2 |  | Discussion: replies, category filter, anonymous posting, my activity | 2026-10-12 | 2026-10-31 | 20
S2 | Khan | As a user, I can open a post and reply to the discussion. | 2026-10-12 | 2026-10-30 | 19
S2 | Khan | Create replies table linked to post and author | 2026-10-12 | 2026-10-13 | 2
S2 | Khan | Build reply API; update reply count in the same transaction | 2026-10-14 | 2026-10-18 | 5
S2 | Khan | Create post detail screen showing the full discussion | 2026-10-19 | 2026-10-23 | 5
S2 | Khan | Add reply composer so new replies appear in the thread | 2026-10-24 | 2026-10-27 | 4
S2 | Khan | Review & check-in | 2026-10-28 | 2026-10-30 | 3
S2 | Khan | Document | 2026-10-26 | 2026-10-30 | 5
S2 | Ayman | As a user, I can browse and filter posts by category. | 2026-10-12 | 2026-10-30 | 19
S2 | Ayman | Add category filter to the feed API | 2026-10-12 | 2026-10-16 | 5
S2 | Ayman | Build category filter chips on the feed screen | 2026-10-17 | 2026-10-21 | 5
S2 | Ayman | Show category label on post cards and post detail | 2026-10-22 | 2026-10-25 | 4
S2 | Ayman | Handle categories with no posts (empty state) | 2026-10-26 | 2026-10-27 | 2
S2 | Ayman | Review & check-in | 2026-10-28 | 2026-10-30 | 3
S2 | Ayman | Document | 2026-10-26 | 2026-10-30 | 5
S2 | Jalal | As a user, I can publish a post anonymously. | 2026-10-12 | 2026-10-30 | 19
S2 | Jalal | Add is_anonymous field while keeping the internal author link | 2026-10-12 | 2026-10-13 | 2
S2 | Jalal | Strip author identity from API responses for anonymous posts | 2026-10-14 | 2026-10-17 | 4
S2 | Jalal | Add Anonymous Post toggle to the post composer | 2026-10-18 | 2026-10-20 | 3
S2 | Jalal | Show 'Anonymous' on feed/detail; label author's own replies 'Anonymous (OP)' | 2026-10-21 | 2026-10-24 | 4
S2 | Jalal | Write privacy tests: no identity leaks through API or UI | 2026-10-25 | 2026-10-27 | 3
S2 | Jalal | Review & check-in | 2026-10-28 | 2026-10-30 | 3
S2 | Jalal | Document | 2026-10-26 | 2026-10-30 | 5
S2 | Wesley | As a user, I can view my own posts and replies. | 2026-10-12 | 2026-10-30 | 19
S2 | Wesley | Build my-activity API (visible only to the owner) | 2026-10-12 | 2026-10-16 | 5
S2 | Wesley | Create My Posts & Replies screen | 2026-10-17 | 2026-10-21 | 5
S2 | Wesley | Enforce ownership checks so users can't modify others' content | 2026-10-22 | 2026-10-25 | 4
S2 | Wesley | Include my anonymous posts, marked as anonymous | 2026-10-26 | 2026-10-27 | 2
S2 | Wesley | Review & check-in | 2026-10-28 | 2026-10-30 | 3
S2 | Wesley | Document | 2026-10-26 | 2026-10-30 | 5
S2 | All | ◆ Sprint 2 review & retrospective | 2026-10-31 | 2026-10-31 | 1
Sprint 3 |  | AI summary twist, likes, testing, final demo | 2026-11-01 | 2026-11-19 | 19
S3 | Jalal | As a user, I can view an AI summary once a post reaches the reply threshold. | 2026-11-01 | 2026-11-18 | 18
S3 | Jalal | Create summaries table (text, generated time, reply count at generation) | 2026-11-01 | 2026-11-02 | 2
S3 | Jalal | Build server-side LLM service; API key kept in server environment | 2026-11-03 | 2026-11-07 | 5
S3 | Jalal | Design summary prompt: send reply text only, no account info | 2026-11-08 | 2026-11-10 | 3
S3 | Jalal | Build summarize endpoint with threshold check and error handling | 2026-11-11 | 2026-11-15 | 5
S3 | Jalal | Review & check-in | 2026-11-16 | 2026-11-18 | 3
S3 | Jalal | Document | 2026-11-14 | 2026-11-18 | 5
S3 | Khan | As a user, I can refresh the AI summary after new replies are added. | 2026-11-01 | 2026-11-18 | 18
S3 | Khan | Detect replies added since the last summary | 2026-11-01 | 2026-11-04 | 4
S3 | Khan | Build refresh endpoint that uses the updated set of replies | 2026-11-05 | 2026-11-08 | 4
S3 | Khan | Prevent duplicate refreshes (in-progress lock and rate limit) | 2026-11-09 | 2026-11-12 | 4
S3 | Khan | Show Refresh button only when new replies exist | 2026-11-13 | 2026-11-15 | 3
S3 | Khan | Review & check-in | 2026-11-16 | 2026-11-18 | 3
S3 | Khan | Document | 2026-11-14 | 2026-11-18 | 5
S3 | Ayman | As a user, I can see the summary clearly labeled as AI-generated. | 2026-11-01 | 2026-11-18 | 18
S3 | Ayman | Build summary panel on the post detail screen | 2026-11-01 | 2026-11-06 | 6
S3 | Ayman | Add 'AI-generated' label and generation timestamp | 2026-11-07 | 2026-11-09 | 3
S3 | Ayman | Hide the summary option below the reply threshold | 2026-11-10 | 2026-11-11 | 2
S3 | Ayman | Add loading and error states for summary requests | 2026-11-12 | 2026-11-15 | 4
S3 | Ayman | Review & check-in | 2026-11-16 | 2026-11-18 | 3
S3 | Ayman | Document | 2026-11-14 | 2026-11-18 | 5
S3 | Wesley | As a user, I can like posts and comments. | 2026-11-01 | 2026-11-18 | 18
S3 | Wesley | Create likes table (one like per user per item) | 2026-11-01 | 2026-11-03 | 3
S3 | Wesley | Build like/unlike API for posts and replies | 2026-11-04 | 2026-11-08 | 5
S3 | Wesley | Add like buttons and counts to feed, post detail, and replies | 2026-11-09 | 2026-11-12 | 4
S3 | Wesley | Update like counts instantly without reloading | 2026-11-13 | 2026-11-15 | 3
S3 | Wesley | Review & check-in | 2026-11-16 | 2026-11-18 | 3
S3 | Wesley | Document | 2026-11-14 | 2026-11-18 | 5
S3 | All | As a team, we deliver a tested, demo-ready release. | 2026-11-01 | 2026-11-18 | 18
S3 | All | End-to-end testing of all main workflows | 2026-11-01 | 2026-11-06 | 6
S3 | All | Fix bugs found in testing | 2026-11-07 | 2026-11-11 | 5
S3 | All | Prepare final presentation and demo | 2026-11-12 | 2026-11-15 | 4
S3 | All | Final documentation and backlog update | 2026-11-16 | 2026-11-18 | 3
S3 | All | ◆ Final demo & submission | 2026-11-19 | 2026-11-19 | 1
Owner colors
Jalal
Wesley
Khan
Ayman
All (whole team)
Task dates are a starting plan: development tasks are laid out in sequence in proportion to their estimated hours; review and documentation fill the last days before each sprint review.

## Sprint 1
Owner | User Story | Task | Points | Est. (Hrs) | Hrs Left (9/28) | Hrs Left (10/2) | Hrs Left (10/6) | Hrs Left (10/10)
Jalal | As a user, I can register for an account with a unique username and email. |  | 5 | 24
|  | Set up backend project, database, and users table |  | 6
|  | Build registration API with password hashing and duplicate checks |  | 6
|  | Create registration screen UI |  | 5
|  | Add input validation and error messages |  | 3
|  | Review & check-in |  | 2
|  | Document |  | 2
Wesley | As a user, I can log in and stay logged in while I use the app. |  | 5 | 22
|  | Build login API with token-based session |  | 6
|  | Create login screen UI |  | 4
|  | Persist session across app restarts and add logout |  | 4
|  | Require login before creating posts or replies |  | 4
|  | Review & check-in |  | 2
|  | Document |  | 2
Khan | As a user, I can create a post with a title, description, and category. |  | 5 | 23
|  | Create posts and categories tables; seed predefined categories |  | 5
|  | Build create-post API (logged-in users only) |  | 5
|  | Create post composer screen with category picker |  | 6
|  | Validate title, description, and required category |  | 3
|  | Review & check-in |  | 2
|  | Document |  | 2
Ayman | As a user, I can browse posts created by other users in a feed. |  | 5 | 23
|  | Set up mobile app skeleton and screen navigation |  | 5
|  | Build feed API (newest first, paginated) |  | 5
|  | Create feed screen with post cards (title, category, author, reply count) |  | 6
|  | Add pull-to-refresh plus loading and empty states |  | 3
|  | Review & check-in |  | 2
|  | Document |  | 2
Total |  |  | 20 | 92
Sprint 1: 9/22/2026 – 10/11/2026. Goal: Foundation: accounts, login, create post, post feed.
Fill in Hrs Left on task rows at each check-in; story and total rows add up automatically.

## Sprint 2
Owner | User Story | Task | Points | Est. (Hrs) | Hrs Left (10/16) | Hrs Left (10/20) | Hrs Left (10/24) | Hrs Left (10/29)
Khan | As a user, I can open a post and reply to the discussion. |  | 8 | 24
|  | Create replies table linked to post and author |  | 3
|  | Build reply API; update reply count in the same transaction |  | 6
|  | Create post detail screen showing the full discussion |  | 6
|  | Add reply composer so new replies appear in the thread |  | 5
|  | Review & check-in |  | 2
|  | Document |  | 2
Ayman | As a user, I can browse and filter posts by category. |  | 5 | 18
|  | Add category filter to the feed API |  | 4
|  | Build category filter chips on the feed screen |  | 5
|  | Show category label on post cards and post detail |  | 3
|  | Handle categories with no posts (empty state) |  | 2
|  | Review & check-in |  | 2
|  | Document |  | 2
Jalal | As a user, I can publish a post anonymously. |  | 8 | 24
|  | Add is_anonymous field while keeping the internal author link |  | 3
|  | Strip author identity from API responses for anonymous posts |  | 5
|  | Add Anonymous Post toggle to the post composer |  | 3
|  | Show 'Anonymous' on feed/detail; label author's own replies 'Anonymous (OP)' |  | 5
|  | Write privacy tests: no identity leaks through API or UI |  | 4
|  | Review & check-in |  | 2
|  | Document |  | 2
Wesley | As a user, I can view my own posts and replies. |  | 5 | 20
|  | Build my-activity API (visible only to the owner) |  | 5
|  | Create My Posts & Replies screen |  | 5
|  | Enforce ownership checks so users can't modify others' content |  | 4
|  | Include my anonymous posts, marked as anonymous |  | 2
|  | Review & check-in |  | 2
|  | Document |  | 2
Total |  |  | 26 | 86
Sprint 2: 10/12/2026 – 10/31/2026. Goal: Discussion: replies, category filter, anonymous posting, my activity.
Fill in Hrs Left on task rows at each check-in; story and total rows add up automatically.

## Sprint 3
Owner | User Story | Task | Points | Est. (Hrs) | Hrs Left (11/5) | Hrs Left (11/9) | Hrs Left (11/13) | Hrs Left (11/17)
Jalal | As a user, I can view an AI summary once a post reaches the reply threshold. |  | 8 | 23
|  | Create summaries table (text, generated time, reply count at generation) |  | 3
|  | Build server-side LLM service; API key kept in server environment |  | 6
|  | Design summary prompt: send reply text only, no account info |  | 4
|  | Build summarize endpoint with threshold check and error handling |  | 6
|  | Review & check-in |  | 2
|  | Document |  | 2
Khan | As a user, I can refresh the AI summary after new replies are added. |  | 5 | 20
|  | Detect replies added since the last summary |  | 4
|  | Build refresh endpoint that uses the updated set of replies |  | 5
|  | Prevent duplicate refreshes (in-progress lock and rate limit) |  | 4
|  | Show Refresh button only when new replies exist |  | 3
|  | Review & check-in |  | 2
|  | Document |  | 2
Ayman | As a user, I can see the summary clearly labeled as AI-generated. |  | 5 | 16
|  | Build summary panel on the post detail screen |  | 5
|  | Add 'AI-generated' label and generation timestamp |  | 2
|  | Hide the summary option below the reply threshold |  | 2
|  | Add loading and error states for summary requests |  | 3
|  | Review & check-in |  | 2
|  | Document |  | 2
Wesley | As a user, I can like posts and comments. |  | 5 | 20
|  | Create likes table (one like per user per item) |  | 3
|  | Build like/unlike API for posts and replies |  | 5
|  | Add like buttons and counts to feed, post detail, and replies |  | 5
|  | Update like counts instantly without reloading |  | 3
|  | Review & check-in |  | 2
|  | Document |  | 2
All | As a team, we deliver a tested, demo-ready release. |  | 3 | 26
|  | End-to-end testing of all main workflows |  | 8
|  | Fix bugs found in testing |  | 8
|  | Prepare final presentation and demo |  | 6
|  | Final documentation and backlog update |  | 4
Total |  |  | 26 | 105
Sprint 3: 11/1/2026 – 11/19/2026. Goal: AI summary twist, likes, testing, final demo.
Fill in Hrs Left on task rows at each check-in; story and total rows add up automatically.